## Sheet1
Matrix of Organized Participation and Roles - MAPP - Regional Approach (MODEL #1)
Core Team: a small group of individuals from the health departments and regional and/or local public health system (PHS) partners that are responsible for organizing the process and moving it forward. This includes the primary inidivudals that provide staff support to the committee (i.e.; facilitator, scribe, etc) Local CHA/CHIP Committee: the county specific representatives that provide input to the Core Team representatives and assist with creating relevance of the regional level CHA/CHIP to the county level community as necessary. Core Team Subcommittees: Team members designated to draft various elements necessary for the organization of the process and provide preliminary ideas from which to work. To be tasked with duties better done in small groups than large for review by Entire Core Team. These subcommittees may recruit individuals with expertise as needed that are not members of the Core Team. Local CHA/CHIP Subcommittees: Recruited and assigned on an as needed basis by Core Team or Local Committee. May also be used to broaden community participation.
Guiding Principle: Broad Community Participation is Essential
MAPP Phase | Core Team | Local CHA/CHIP Committee | Core Team Subcommittees | Local CHA/CHIP Subcommittees
Members | 1 HD rep each county and 1 Public Health System (PHS) partner each county | 8-10 PHS partners and 2-4 community partners | Minimum 1 each HD and PHS | As needed
Organize for Success - Partnership Development | Begin the process and move it forward | Assist with identification of community voices | Draft roles delineation for members
| Organize and plan the process | Provide input to core team members | Draft Timeline
| Identify resources | Identify additional resources | Develop meeting agendas
| Recruit membersip for committees |  | Prepare media materials including recruitment packet
Determine subcommittee needs
Participate on at least one subcommittee
Select a facilitator to work with project
Visioning | Plan visioning session | Participate in visioning phase | To be determined | To be determined
| Ensure facilitation and work with facilitator in preparing for session | Develop plan for gaining broad community support
| Summarize results of meetings | Identify participants
Draft vision and values statements
Community Themes and Strengths | Support Committee and Subcommittee Activities | Oversee subcommittee activities | To be determined as needed | To be determined as needed
Compile information gathered for Core Team
Participate as needed in activities
Local Public Health System Assessment | Compile subcommittee and local committee information | Respond to performance measures instrument | To be determined as needed | To be determined as needed
| Support committee and subcommittee activities | Discuss results/identfiy challenges and opportunities
| Identify county overlap and partners who also work regionally | Assist with data collection
Community Health Status Assesment | Support committee and subcommittee activities | Select locally appropriate indicators | Recommend indicators | To be determined as needed
| Determine regional and local presentation of data | Provide input into Profile development
| Finalize indicator selection | Assist with data collection
Make presentation to communities
Forces of change Assessment | Prepare for and plan brainstorming session(s) | Paticipate in brainstorming session | To be determined | To be determined
| Ensure facilitation and work with facilitator in prep | Conduct local interviews
Identify threats and opportunities for each force
Summarize and compile results of meetings
Identify strategic issues | Compile results for four assessments | Review and comment on draft issues paper | To be determined | To be determined
Draft strategic issues
Formulate Goals and Strategies | Prepare information for developing Goals and Strategies | Provide input into CHIP | Identify best practices | To be determined
| Draft Planning Report | Assist with community and system partner buy in to CHIP
Review Draft and comment
Action Cycle | Prepare plan for CHA/CHIP cycle
Note on C14: Ashley: Spelling needs corrected for visioning