## Sheet1
Total Estimated Minimum and Maximum Costs for Phases 1-5 (18 months)
Costs exclude data collection costs that are contingent on subcommittee decisions and availability of data.
Phases | Minimum Costs | Maximum Costs
1-2 | 61636.5 | 150486.5
3 | 27683.75 | 70883.75
4-5 | 3203 | 29878
Total Costs | 92523.25 | 251248.25
Organizing for Success/Visioning
|  | Minimum Costs |  |  |  |  | Maximum Costs
Funding Sources: D=DHHS; P=Partner; F=Foundation Grant; N=NACCHO; C=County Appropriations; H=Hospital Community Benefit
Activity | Details | Resource | Units/ Staff Hrs | Cost per Unit | Total Cost | Funding Source | Resource | Units/ Staff Hrs | Cost per Unit | Total Cost | Funding Source
Staff Time | Identify partners | .50 FTE for 1.5 year (e.g. epidemiologist, health planner, and/or health educator) | 0.75 | 80000 | 60000 | D | 1 FTE for 1.5 year (e.g. epidemiologist, health planner, and/or health educator) | 1.5 | 80000 | 120000 | D,P
Create committee structure
Identify MAPP Committee members
Identify key sponsors
Identify previous visioning efforts
Design visioning process
Plan first meeting
Invite partners to meeting
Follow-up after meeting
Compile and finalize visioning
Evaluate effectiveness of phases
Orientation & Visioning Meeting | Meeting space | 1 venue for 1 day | 1 | 0 | 0 | D,P | 1 hotel rm for 1 day | 1 | 500 | 500 | C,F,H
| Audio/Visual | Laptop/projector | 1 | 0 | 0 | D | AV supply for 1 day | 1 | 100 | 100 | C,F
| Copy costs for meeting materials | 15pg x 100ppl=1500pg | 1500 | 0.05 | 75 | D | 15pg x 100ppl=1500pg | 1500 | 0.05 | 75 | D
| Food (breakfast & lunch) | Food for 100 ppl | 100 | 15 | 1500 | D,P | Food for 100 ppl | 100 | 75 | 7500 | D,P,F,H
| Postage costs | 150 invitations | 150 | 0.41 | 61.5 | D | 150 invitations | 150 | 0.41 | 61.5 | D
| Facilitator | 1 facilitator for 20 hrs | 20 | 0 | 0 | D,P,N | 1 facilitator for 20 hrs | 20 | 100 | 2000 | C,F,H
Marketing | Promote vision online | website | 1 | 0 | 0 | D,P | website | 1 | 0 | 0 | D,P
| Print vision on cards for distribution | [5 empty] | print 1,000 w/ graphics | 1000 | 0.25 | 250 | D,P,F
[7 empty] | graphic design | 1 | 2000 | 2000
| Newspaper advertisement | [5 empty] | 1/4 pg color in Gazette | 1 | 2800 | 2800 | D,P,F,H
[7 empty] | 1 pg color in Gazette | 1 | 11000 | 11000 | D,P,F,H
| Print full-color glossy flyers |  |  |  | 0 |  | print 1,000 w/ graphics | 1000 | 0.75 | 750 | D,P,F
| Create a brand | partner designed logo | 1 | 0 | 0 | P | professional logo | 1 | 1000 | 1000 | C,F
Training | Facilitator training for MAPP staff | [5 empty] | 1 training for 1 staff | 1 | 450 | 450 | C,F
| NPHPSP training for MAPP staff | 1 training w/scholarship | 1 | 0 | 0 | N | 1 training for 1 staff | 1 | 1000 | 1000 | C,F
| Dialogue training for MAPP staff | [5 empty] | 1 training for 1 staff | 1 | 1000 | 1000 | C,F
|  |  |  | Total | 61636.5 |  |  |  | Total | 150486.5
Four Assessments
|  | Minimum Costs |  |  |  |  | Maximum Costs
Funding Sources: D=DHHS; P=Partner; F=Foundation Grant; N=NACCHO; C=County Appropriations; H=Hospital Community Benefit
Activity | Details | Resource | Units/ Staff Hrs | Cost per Unit | Total Cost | Funding Source | Resource | Units/ Staff Hrs | Cost per Unit | Total Cost | Funding Source
Staff Time for all Four MAPP Assessments | Organize & facilitate subcommittees | Additional .50 FTE for 6 months | 0.25 | 80000 | 20000 | D | Additional 1 FTE for 6 months | 0.5 | 80000 | 40000 | D,P
Collect existing assessment data
Organize & analyze data
Create a system for updating data
Meeting minutes & correspondence
Plan & convene NPHPSP meeting
Train facilitators & recorders for NPHPSP meeting
Evaluate effectiveness of phase 3
Subcommittee Meetings | Meeting space | 3 mtgs/mo. for 5mo. | 15 | 0 | 0 | D, P | 3 time/mo. for 5mo. | 15 | 0 | 0 | D, P
| Copy costs for meeting materials | 15 pgs x 15 mtgs=225 pgs | 225 | 0.05 | 11.25 | D, P | 15 pgs x 15 mtgs=225 pgs | 225 | 0.05 | 11.25 | D, P
| Conference calls | 6 x 60 min. calls | 360 | 0.1 | 36 | D, P | 6 x 60 min. calls | 360 | 0.1 | 36 | D, P
| Snacks (4 subcommittee of 15 ppl) | (15 x 4) x 15 mtgs=900 | 900 | 5 | 4500 | D,P | (15 x 4) x 15 mtgs=900 | 900 | 5 | 4500 | D,P
Data collection (methods will depend on subcommittee decisions) | Focus groups
Survey development
Survey dissemination
Interviews
Town hall meetings
Other primary data collection
Data analysis
Data access costs
NPHPSP Completion Meeting | Meeting space | 1 venue for 1-2 day(s) | 2 | 0 | 0 | D,P | 1 hotel rm for 2 days | 2 | 500 | 1000 | C,F
| Audio/Visual | Laptop/projector | 1 | 0 | 0 | D | AV supply for 2 days | 2 | 100 | 200 | C,F
| Copy costs for meeting materials | 15pg x 100ppl=1500pg | 1500 | 0.05 | 75 | D | 15pg x 100ppl=1500pg | 1500 | 0.05 | 75 | D
| Food (breakfast & lunch) | Food (100 ppl, 2days) | 200 | 15 | 3000 | D,P | Food (100 ppl, 2days) | 200 | 75 | 15000 | D,P,F
| Postage costs | 150 invitations | 150 | 0.41 | 61.5 | D | 150 invitations | 150 | 0.41 | 61.5 | D
| Facilitators | 5 facilitators for 20 hrs | 100 | 0 | 0 | D,P,N | 5 facilitator for 20 hrs | 100 | 100 | 10000 | C,F,H
|  |  |  | Total | 27683.75 |  |  |  | Total | 70883.75
Identifying Strategic Issues and Formulating Goals and Strategies
|  | Minimum Costs |  |  |  |  | Maximum Costs
Funding Sources: D=DHHS; P=Partner; F=Foundation Grant; N=NACCHO; C=County Appropriations; H=Hospital Community Benefit
Activity | Details | Resource | Units/ Staff Hrs | Cost per Unit | Total Cost | Funding Source | Resource | Units/ Staff Hrs | Cost per Unit | Total Cost | Funding Source
Staff Time for all Four MAPP Assessments | Assist MAPP Committee in planning | Staff hired for previous phases | 0.75 |  |  | D | Staff hired for previous phases | 1 |  |  | D,P
Organize data collected in phase 3
Prepare for phase 4/5 meeting
Phase 4-5 Planning Meeting | Meeting space | 1 full-day meeting | 8 | 0 | 0 | D, P | 1 full-day meeting | 8 | 0 | 0 | D, P
| Copy costs for meeting materials | 50 pgs x 12 ppl=600 pgs | 600 | 0.05 | 30 | D, P | 50 pgs x 12 ppl=600 pgs | 600 | 0.05 | 30 | D, P
| Food (breakfast & lunch) | Food (15ppl) | 15 | 15 | 225 | D,P | Food (15ppl) | 15 | 50 | 750 | D,P,F
Phase 4-5 Meeting | Meeting space | 1 day meeting | 1 | 0 | 0 | D,P | 1 hotel rm for 1 day | 1 | 500 | 500 | C,F,H
| Audio/Visual | Laptop/projector | 1 | 0 | 0 | D | AV supply for 1 day | 1 | 100 | 100 | C,F
| Copy costs for meeting materials | 15pg x 100ppl=1500pg | 1500 | 0.05 | 75 | D | 15pg x 100ppl=1500pg | 1500 | 0.05 | 75 | D
| Food (breakfast & lunch) | Food (100 ppl, 1 day) | 100 | 15 | 1500 | D,P | Food (100 ppl, 1 day) | 100 | 75 | 7500 | D,P,F
| Postage costs | 150 invitations | 150 | 0.41 | 61.5 | D | 150 invitations | 150 | 0.41 | 61.5 | D
| Facilitators | 1 facilitator for 20 hrs | 20 | 0 | 0 | D,P,N | 1 facilitator for 20 hrs | 20 | 100 | 2000 | C,F,H
Marketing | Design CHIP report | 25 pg report | 1 | 0 | 0 | D | professionally designed | 1 | 2000 | 2000 | D,C,F,H
| Print CHIP report | Print 1000 (25 pgs) | 25000 | 0.05 | 1250 | D | 1000 outsourced reports | 1000 | 1 | 1000 | D,C,F,H
[7 empty] | graphic design | 1 | 2000 | 2000 | D,C,F,H
| Mail reports to partners | 150 invitations | 150 | 0.41 | 61.5 | D | 150 invitations | 150 | 0.41 | 61.5 | D
| Newspaper advertisement | [5 empty] | 1/4 pg color in Gazette | 1 | 2800 | 2800 | D,P,F,H
[7 empty] | 1 pg color in Gazette | 1 | 11000 | 11000 | D,P,F,H
| Post information online | website | 1 | 0 | 0 | D,P | website | 1 | 0 | 0 | D,P
|  |  |  | Total | 3203 |  |  |  | Total | 29878