## Project Timeline
ROADMAP TO ACCREDITATION
| ENTER START DATE: | 2017-05-08
Id | ACTIVITY | START | END | NOTES
-20 | Project Start | 2017-01-01 |  | The kick off to this project-ACCREDITATION READINESS-was obtaining the ASI grant in September of 2016. 4 members of our A Team were able to attend the Open Forum in April of 2017 and brought back, tools, resources, excitement and a realistic perspective of what it will take our health department to become accredIted. By attending the Open Forum and having conversations with other health departments going through accreditation, or who are already accredited, we have a greater understanding of what it will take knowing where our staff is currently at with skills, knowledge and buy in. I think "slow and steady wins the race" would be a good motto for us at this time. Barriers that have come up since receiving the grant are lose of staff due to death, retirements and newly hired core staff. We do have a renewed energy around becoming accredited. I feel that is because we have developed a timeline that is realistic and we feel competent that it is achievable.
-19 | 2.4 Workforce Development Plan | 2017-05-08 | 2017-05-16 | This plan is almost complete. Final revisions to be made on May 16, 2017.
-18 | Assign Domain Leads | 2017-05-08 | 2017-05-10 | Each measure has a lead. One lead from each Domain will be chosen to be the Doain Champion. Whil all have been identified we will wait to approach some staff as we have a key support staff who recently passed away; the office manager is retiring at the end of July, and our bookkeeper is retiring in March of 2018. Therefore the only support staff we will have with experience is our new office manager who started one year ago. The ripple effect of these support staff changes have been felt by all staff. Our accreditation readiness efforts have been realistically adjusted to promote success.
-17 | Assign Domain of the Month | 2017-05-08 | 2017-05-10 | Domain Lead will present their Domain at an all staff meeting. This will assist with all staff being aware of what each Domain is and their role in it. We will also be covering topics such as data analysis, health equity, quality Improvement--topics that are ingrained in the standards.
-16 | Domain of the Month | 2017-07-01 | 2017-08-12 | TBD
-15 | Domain of the Month | 2017-07-01 | 2017-08-13 | TBD
-14 | Domain of the Month | 2017-07-01 | 2017-08-14 | TBD
-13 | Domain of the Month | 2017-07-01 | 2017-08-15 | TBD
-12 | Domain of the Month | 2017-07-01 | 2017-08-16 | TBD
-11 | Domain of the Month | 2017-07-01 | 2017-08-17 | TBD
-10 | Domain of the Month | 2017-07-01 | 2017-08-18 | TBD
-9 | Domain of the Month | 2017-07-01 | 2017-08-19 | TBD
-8 | Domain of the Month | 2017-07-01 | 2017-08-20 | TBD
-7 | Domain of the Month | 2017-07-01 | 2017-08-21 | TBD
-6 | Domain of the Month | 2017-07-01 | 2017-08-22 | TBD
-5 | Domain of the Month | 2017-07-01 | 2017-08-23 | TBD
-4 | Choose additional A Team Members | 2017-05-08 | 2017-06-19 | Jackie is retiring; Jenna will be busy with rebuilding her support staff; need additional members. Will choose from those who are determined to be champions of each standard.
-3 | Choose Domain to do as A Team | 2017-05-08 | 2017-06-19 | The A Team will complete the documentation selection as a team. This domain will then be used as an example for the rest of the teams when they begin the process of documentaiton selection.
-2 | A Team Domain -Complete | 2017-05-09 | 2018-06-30 | The A Team will have their Domain complete by this date. This will then be a monthly presentation to all staff.
-1 | Kick off for remaining Domain Teams |  | 2018-01-01 | All Domain Teams will begin collecting documentation as they feel able and have the capacity to do so.
| Begin preparation for Strategic Planning | 2018-01-01 | 2018-03-31 | Our current Strategic Plan was done by updating the prior plan (2012-2015). The current Strategic Plan is dates 2015-2018. Preparation will include training for the accreditation coordinator in strategic planning.
| Strategic Planning Process | 2018-06-01 | 2018-12-31 | Complete Strategic Plan
| Community Health Assessment | 2017-01-01 | 2017-10-31 | Completed CHA & Community Engagment Sessions
3 | Community Health Improvement Plan | 2017-11-01 | 2018-03-01 | DATED 2018-2021 (CURRENT PLAN IS 2015-2018)
4 | Submit Statement of Intent | TBD | TBD
5 | Submit Prerequisites to PHAB | TBD | TBD

## calcs (hidden)
*** This sheet should remain hidden ***
|  | Today: | 2017-06-05
5
|  | # of rows | 26
#N/A
#N/A
#N/A
|  | Window Activities: | 3 | #N/A
|  |  | 9 | #N/A
|  |  | 6 | #N/A
#N/A
#N/A
#N/A
|  |  |  | -2 | #N/A
|  |  |  | -1 | #N/A
|  |  |  | 0 | #N/A
|  |  |  | #N/A | #N/A
|  |  |  | #N/A | #N/A
|  |  |  | #N/A | #N/A
|  |  |  | #N/A | -2
|  |  |  | #N/A | -1
|  |  |  | #N/A | 0
|  | Calc Window Start | 2017-09-28
|  | Offset | 143
|  | Start | 2017-05-08
|  | Window | 30
Position | Series | Activity Id | Activity | 2017-09-28 | 2017-09-29 | 2017-09-30 | 2017-10-01 | 2017-10-02 | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28
11.3 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10.3 | 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9.3 | 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8.3 | 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7.3 | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6.3 | 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5.3 | 7 | -2 | A Team Domain -Complete | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3
4.3 | 8 | -1 | Kick off for remaining Domain Teams | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3 | 4.3
3.3 | 9 | 0 | #N/A | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3
|  |  |  | 2017-09-28 | 2017-09-29 | 2017-09-30 | 2017-10-01 | 2017-10-02 | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -2 | A TEAM DOMAIN -COMPLETE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -1 | KICK OFF FOR REMAINING DOMAIN TEAMS | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2017-09-28 | 2017-09-29 | 2017-09-30 | 2017-10-01 | 2017-10-02 | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27
|  |  | Current Day | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-09-01 | 0.5 | 0.5 | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | Sep 2017 - Top Band | 13 | 13 | 13 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-10-01 | #N/A | #N/A | #N/A | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Oct 2017 - Top Band | #N/A | #N/A | #N/A | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
|  |  | 2017-09-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2017-10-02 | #N/A | #N/A | #N/A | #N/A | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  |  | 3 | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI
|  |  |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
|  |  |  | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27