Timeline for School-Located Influenza Immunization Programs

January-February

Assess interest of schools – visit with superintendent, principals, school nurse(s)

Assess interest of public health county administration

Designate team leaders under ICS

Decide which vaccine(s) will be used

Decide if will vaccinate staff

Decide on vaccines to be used, if 2 rounds to be done for <9 yrs

Decide on strategy for vaccinating children with contraindications

Assess availability of vaccine from commercial sources

Clarify vaccine supply/conditions from VFC program

Determine supplies needed

Create budget

Presentations to school board

Presentation to county board, county executive

Secure resources for purchase of vaccine, supplies

Solicit bids/compare prices, place orders for vaccine, purchase supplies

Partner with local medical community

March- June

Identify vaccine storage facility – calculate volume of vaccine, calculate storage capacity, schedule staggered shipments if needed.

Decide on contents of information packet for parents Design permission forms.

Design information forms for parents

Establish a list of languages for translation of forms, contract for translations. Secure VIS in necessary languages from CDC

Secure needed approvals from legal (if needed)

Draft standing orders, get signed by medical director

Plan public relations strategy

Calculate staff numbers

Recruit staff

Establish training protocols

July - August

Get forms printed

Design school website(s), post

Create public health information page

Schedule clinics at each participating school

Schedule staff

Create public information materials

Schedule training sessions

September – November

Conduct training sessions

Distribute materials to parents

Collect permission forms

Review permission forms for contraindications and ensure correctly filled out

Conduct clinics

December

Thank teachers, volunteers and others who participated

Debriefing

December- March

Evaluate using absenteeism rates for students and staff